## Sheet1
Promoting Prevent Agenda within Employment and Skills - Assessment of Risk and Action Plan 21-22
Prevent Area | Potential Risk | Actions taken to Minimise Risk to date | Evidence | Further Actions | Staff Leads | By When
Staff & Volunteers | Lack of awareness resulting in staff/volunteers overlooking/missing risks | Safe recruitment procedures followed including appropriate staff DBS checked. | Central DBS Checks summary | All new E & S staff to do new Radicalisation I-Learn module including hourly paid and update central CPD log. Objective noted on appraisal records | Senior Officers | 2020-10-31
|  | Staff induction covers Safeguarding training | Volunteer induction programme | New volunteers to complete radicalisation module | AR and MMcD | 2020-10-01
|  | Promotion of Safeguarding Policy to volunteers | Displayed Safeguarding Poster on all sites | Volunteer meetings to include Prevent awareness | MMcD/AR | ongoing
|  | Family Learning volunteers undertook the Prevent practitioners training module through ETF online. Also covered and British Values, safeguarding, E and D etc) in FL volunteer meetings. | FL Volunteer Coordinator records | ESL classroom volunteers to all undertake the Prevent Practioners training module through ETF. | AR | 2020-10-01
Partnership | Sub-contracted partners unaware of their duty and lack of awareness resulting in partner staff overlooking/missing risks | Contractual requirement | AEB Contract |  | MS | 2020-08-01
|  | Positive promotion of E and D themes including British Values | E and D termly newsletter | Maintain high level of promotion within each termly newsletter | MMcD | 2020-07-01
|  | Partner tutors all completed EFT online Prevent Awareness training | QCP monitoring records |  | MMcD | 2020-12-01
|  | Tutors all DBS checked. | Central log of DBS checks | All new staff to have DBS check reference noted on database at start of employment. | Appropriate Senior Officer | On going
|  | Awareness of Police Prevent Leads. | British Values posters displayed in every centre | Maximise opportunities to deepen learners' understanding of British Values. See QIP action. | MMcD | 2020-07-01
On-line Safety | Learners accessing/downloading/forwarding inappropriate material on line | Online Safety Policy Statement promoted to learners including cyber-bullying | Online Safety Policy with explicit reference to Prevent duty. | Promote to all learners throughout academic year. | MMcD | 2020-09-01
|  | Promotion of online safety built into induction | Induction Policy
|  | Posters up in all learning environments | Safeguarding Poster with explicit reference to Prevent duty. | Maintain promotion of Safeguarding and Learner Disclosure (and the difference between) to sub-contracted partners. | CL | 2020-10-01
|  | Council has filtering/firewall systems to prevent staff/students/visitors accessing extremist websites and material. Includes wifi. | Council ICT systems
|  |  |  | Code of conduct notification up in all Work Zones re the acceptable use of our PC. | AR | 2020-09-01
Staff Training | Lack of awareness resulting in staff overlooking/missing risks. Specific risk with hourly paid staff not accessing the same support mechanisms as permanent staff | All E & S staff trained in Prevent Awareness | Central CPD Log
|  |  |  | All new E&S staff to complete Radicalisation I learn module as part of their induction and update central CPD log. | Senior Officers | on going
All E & S staff trained in Safeguarding
Tutors completed ETF online training
|  | Staff supported to exemplify British Values in their management, teaching and general behaviour | OTA records, E and D newsletters | Build on developing learner awareness of how to apply British Values within their learning and their lives. | QCP team | on going
|  | Tutor Handbook contains reference to our duties under Prevent | Tutor Handbook | Update Learner Handbook for 20/21 | QCP team | 2020-08-01
Leadership | Insufficient responsibility taken for the promotion and vigilance of our Prevent duty putting staff, partners and learners at risk | High priority of Prevent/Safeguarding within SAR, QUIP and SET | Copies of SAR, QUIP and Minutes of SEMT meetings | QIP to include actions as appropriate regarding deepening learner's understanding and their application in their learning and lives and monitor progress. | MMcD | 2020-12-01
|  | Overaching approach to Safeguarding Policy for E and S including our approach to Prevent | Policy Statement circulated to staff via email. | Reinforce promotion of safeguarding and learner disclosure to partners at termly meeting. | CL | on going
E and S management team all undertaken Prevent training
Awareness of central LA Prevent Lead - Gavin Butler
Member of Council's Channel Panel.
Incident Management | Lack of recording leading to incidents escalating, missing trends or strategic approach to actions required. | Central Log of Incidents including Prevent kept, monitored and updated. No reporting under Prevent this year to date. | Central Safeguarding/Disclosure Log | Refresh awareness of all procedures with team for new academic year. | CL | 2020-09-01
|  | Council has emergency planning team with associated critical incident management plan. | LA Critical Incident Plan
|  | Staff have specific Critical Incident Plan for Work Zones | Skills and Employment Critical Incident Plan
Building Security | Lack of vigilance/staff awareness in prevent and/or dealing with a terrorist attack | All staff have ID and fobs to access buildings |  | Raise staff awareness of both personal and building safety to prevent unlawful access. | SEMT | 2020-09-01
|  | All visitors have to sign in at sites but generally open access buiidling | AEB Contract
|  | Posters up in all learning environments from Counter Terrorism Policing Unit on what to do in the event of a terrorist attack - Run, Hide Tell | Poster display
|  | Security walk throughs conducted on all sites for Work Choice contract. | Security Walk through records | Carry out annual Building Risk Assessment for all Work Zones | AR | 2020-09-01
|  | All centre noticeboards are managed and regularly updated. Any unofficial postings would be immediately removed. | Work Zone noticeboards/displays | Carry out on-site Contracting & Performance visits to all sub-contractors in years 2-4 of contract to do visual H&S check and confirm safeguarding arrangements. Ensure all Covid 19 risk assessments are completed and recorded | MS | 2020-10-01
Only cleaning/maintenance equipment kept on sites and is stored in accordance with regulations.
Speakers and Events | No screening could lead to inappropriate content being disseminated. | Guest speaker screening form developed and included in central policies and procedures. | External Speaker procedure | External speakers generally not used in Adult Education provision but procedure promoted to partners on our Portal and to usage to be reinforced in year. | MMcD | 2020-10-01
Welfare, Pastoral and Chaplaincy Support | Service users could be vulnerable to grooming without adequate support systems in place. | Pastoral care is largely provided by Tutors within learning environments or Employment Support Officers within the employment mentoring role. All customers are encouraged to discuss anything troubling them. We signpost to referral partners where required. We would provide prayer rooms if requested but so far has not been required. | We're Listening posters on every site. Learner Disclosure Log | Reinforce our Prevent Duty and how grooming leading to extremism could take place within all our settings through constant messages. | SEMT | on going
Safeguarding | Focus on more traditional methods of abuse/harm may mean signs of radicalisation could be missed. | All Safeguarding document makes explicit reference to our duties under the Prevent agenda. Also included in Tutor Handbook and associated learner policies. | Copies of documentation | Update all policies, procedures and learner documentation for 20/21 academic year ensuring every opportunity to promote awareness of the Prevent agenda is taken. | QCP team | 2020-08-01